## Project Timeline
PROJECT TIMELINE: DEPRESSION RISK PREDICTION IN OLDER ADULTS
Relative 24-week plan ¦ Calendar dates are not assigned because the project start date was not provided.
PROJECT PHASE / TASK |  | FIRST SEMESTER | [11 empty] | SECOND SEMESTER
Phase / Task | Timing | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Phase 1: Data Collection and Preprocessing
Identify the data source, review the dataset documentation
Inspect data types, missing values, duplicate records and inconsistent responses
Cleaned analytical dataset
Data dictionary and selected-variable list.
Phase 2: Exploratory Data Analysis
Analyse the distribution of the depression-related outcome among older adults
Create EDA report with descriptive statistics and visualisations
Initial business insights for decision support.
Phase 3: Model Development
Prepare the modelling dataset and separate training and testing data
Documentation of modelling decisions and limitations
Phase 4: Model Evaluation and Optimization
Evaluate candidate models on the test data
Optimise models where appropriate and document their strengths and limitations
Phase 5: Business Insights and Decision Support
Identify groups and factors that may be relevant to further assessment and priorities
Business insights report
Phase 6: Final Refinements and Presentation
Review feedback and identify required improvements
Finalise the model and reports
Prepare the final presentation and check all submission requirements
PHASE MILESTONES
Semester 1: Week 4 | Dataset cleaned and ready for analysis
Semester 1: Week 8 | EDA report and visualisations completed
Semester 1: Week 12 | Initial predictive model developed
Semester 2: Week 4 | Model evaluation completed
Semester 2: Week 8 | Business recommendations completed
Semester 2: Week 12 | Final report, check all submission requirement
Phase 1
Phase 2
Phase 3
Phase 4
Phase 5
Phase 6

## Gantt Template
| Europa project | [5 empty] | Project start: | [7 empty] | 2026-09-21
| VanArsdel, Ltd. | Project lead |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09
| TASK | ASSIGNED TO | PROGRESS | START | END |  | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Define goals | Gokce Aslan | 50% | 2026-09-21 | 2026-09-24 | 4
| Conduct studies | Hayden Cook | 60% | 2026-09-24 | 2026-09-26 | 3
| Establish comms | Jens Martensson | 50% | 2026-09-26 | 2026-09-30 | 5
| Develop charter | Nuria Acevedo | 25% | 2026-09-30 | 2026-10-05 | 6
| Set up team | Olivia Wilson |  | 2026-09-25 | 2026-09-27 | 3
Planning and design
| Create schedule | Gokce Aslan | 50% | 2026-09-26 | 2026-09-30 | 5
| Identify deliverables | Hayden Cook | 50% | 2026-09-28 | 2026-10-03 | 6
| Develop budget | Jens Martensson |  | 2026-10-03 | 2026-10-06 | 4
| Define scope | Nuria Acevedo |  | 2026-10-03 | 2026-10-05 | 3
| Identify risks | Olivia Wilson |  | 2026-10-03 | 2026-10-06 | 4
Final report, dashboard and presentation completed
| Execute tasks | Gokce Aslan | 50% | 2026-10-06 | 2026-10-11 | 6
| Monitor progress | Hayden Cook | 60% | 2026-10-12 | 2026-10-16 | 5
| Manage resources | Jens Martensson | 50% | 2026-10-17 | 2026-10-22 | 6
| Provide updates | Nuria Acevedo | 25% | 2026-10-23 | 2026-10-27 | 5
| Testing and validation | Olivia Wilson | 25% | 2026-10-17 | 2026-10-21 | 5
Evaluation
| Monitor progress | Gokce Aslan | 25% | 2026-10-08 | 2026-10-11 | 4
| Track expenses | Hayden Cook | 25% | 2026-10-11 | 2026-10-15 | 5
| Evaluate progress | Jens Martensson | 50% | 2026-10-16 | 2026-10-19 | 4
| Address risks | Nuria Acevedo | 60% | 2026-10-13 | 2026-10-16 | 4
| Gather feedback | Olivia Wilson | 50% | 2026-10-15 | 2026-10-20 | 6
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]